## Sheet1
ID | PROJECT_ID | NAME | DESCRIPTION | DUE_DATE | CREATED | CREATED_BY | UPDATED | UPDATED_BY
1.1518e+38 | 1.1518e+38 | A1 | A1 | 2026-07-23 | 2026-07-15 12:47 | ARCHI | 2026-07-15 12:47 | ARCHI
11 | 2 | Train the Trainers | Rather than all developers being trained centrally, a select group will be trained. These people will then be responsible for training other developers in their group. | 2026-01-13 | 2026-07-15 11:19 | ARCHIPATEL2632004@GMAIL.COM | 2026-07-15 11:19 | ARCHIPATEL2632004@GMAIL.COM
12 | 2 | All Developers Trained | Train the Trainers will have successfully trained the remaining development team members. | 2026-01-17 | 2026-07-15 11:19 | ARCHIPATEL2632004@GMAIL.COM | 2026-07-15 11:19 | ARCHIPATEL2632004@GMAIL.COM
13 | 3 | Move Data Structures | Move all of the tables and program logic across to the new database | 2026-01-22 | 2026-07-15 11:19 | ARCHIPATEL2632004@GMAIL.COM | 2026-07-15 11:19 | ARCHIPATEL2632004@GMAIL.COM
14 | 3 | Redevelop HR Applications | Build applications to replace the HR functionality currently implemented in older technologies | 2026-01-30 | 2026-07-15 11:19 | ARCHIPATEL2632004@GMAIL.COM | 2026-07-15 11:19 | ARCHIPATEL2632004@GMAIL.COM
15 | 3 | Redevelop Project Tracking Applications | Build applications to replace the project tracking functionality currently running on legacy servers | 2026-02-05 | 2026-07-15 11:19 | ARCHIPATEL2632004@GMAIL.COM | 2026-07-15 11:19 | ARCHIPATEL2632004@GMAIL.COM
16 | 4 | Define Requirements | Work with key stakeholders to define the scope of the project, and design screen flow and data requirements. | 2026-02-08 | 2026-07-15 11:19 | ARCHIPATEL2632004@GMAIL.COM | 2026-07-15 11:19 | ARCHIPATEL2632004@GMAIL.COM
17 | 4 | Build Proof-of-Concept | Create the initial screens and populate with data so key stakeholders can review proposed solution. | 2026-02-15 | 2026-07-15 11:19 | ARCHIPATEL2632004@GMAIL.COM | 2026-07-15 11:19 | ARCHIPATEL2632004@GMAIL.COM
18 | 5 | Define Production App Scope | Based on the results of the POC, define the requirements for the production app. | 2026-02-16 | 2026-07-15 11:19 | ARCHIPATEL2632004@GMAIL.COM | 2026-07-15 11:19 | ARCHIPATEL2632004@GMAIL.COM
19 | 5 | Build Phase 1 of Production Partner Portal App | Develop the modules defined in the first phase of the application. | 2026-02-23 | 2026-07-15 11:19 | ARCHIPATEL2632004@GMAIL.COM | 2026-07-15 11:19 | ARCHIPATEL2632004@GMAIL.COM
20 | 5 | Perform Beta testing with select Partners | Work with a few key partners to trial Phase 1 of the Partner Portal app. | 2026-03-03 | 2026-07-15 11:19 | ARCHIPATEL2632004@GMAIL.COM | 2026-07-15 11:19 | ARCHIPATEL2632004@GMAIL.COM
21 | 5 | Complete Phase 1 Development of Partner Portal app | Based on the results of the Beta program, enhance the application to make production ready. | 2026-03-30 | 2026-07-15 11:19 | ARCHIPATEL2632004@GMAIL.COM | 2026-07-15 11:19 | ARCHIPATEL2632004@GMAIL.COM
22 | 5 | Roll out Phase 1 of Partner Portal app | Go-Live for the Partner Portal application to all partners. | 2026-04-03 | 2026-07-15 11:19 | ARCHIPATEL2632004@GMAIL.COM | 2026-07-15 11:19 | ARCHIPATEL2632004@GMAIL.COM
9.8348e+37 | 1 | ABC | DEF | 2026-02-04 | 2026-07-15 11:19 | ARCHIPATEL2632004@GMAIL.COM | 2026-07-15 11:19 | ARCHIPATEL2632004@GMAIL.COM
1.1517e+38 | 1.1517e+38 | Milestone 1 | Testing Milstones | 2026-07-31 | 2026-07-15 11:35 | ARCHI | 2026-07-15 11:35 | ARCHI
1.1518e+38 | 1.1518e+38 | Milestone 2 | Testing stacked with sub detail | 2026-07-31 | 2026-07-15 12:16 | ARCHI | 2026-07-15 12:16 | ARCHI
1.1518e+38 | 1.1518e+38 | T1 | T1 | 2026-07-23 | 2026-07-15 12:49 | ARCHI | 2026-07-15 12:49 | ARCHI