## Sheet1
ID | PROJECT_ID | MILESTONE_ID | ASSIGNEE | NAME | DESCRIPTION | START_DATE | END_DATE | IS_COMPLETE_YN | CREATED | CREATED_BY | UPDATED | UPDATED_BY
1.1518e+38 | 1.1518e+38 |  | 4 | A1 | A1 | 2026-07-16 | 2026-07-23 | Y | 2026-07-15 12:47 | ARCHI | 2026-07-15 12:47 | ARCHI
51 | 1 |  | 7 | Identify Server Requirements | Determine which databases will be used to install Web development tool for Development, QA, and Production. Also specify which Web Listeners will be used for the three environments. | 2026-01-03 | 2026-01-04 | Y | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM
52 | 1 |  | 5 | Install Web development tool | Install the latest version of Web development tool from the vendor into the databases for Development, QA, and Production. Note: For QA and Production, Web development tool should be configured as "run time" only. | 2026-01-05 | 2026-01-05 | Y | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM
53 | 1 |  | 12 | Configure Web Listeners | Configure the three Web Listeners for Web development tool to support the Dev, QA, and Prod environments. | 2026-01-05 | 2026-01-05 | Y | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM
54 | 1 |  | 11 | Configure Web development tool Instance Administration Settings | Set the appropriate security and configuration settings for the development instance using specified tools. Also set instance settings for QA and Production using the available APIs. | 2026-01-06 | 2026-01-06 | Y | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM
55 | 1 |  | 5 | Define Workspaces | Define workspaces needed for different application development teams. It is important that access be granted to the necessary schemas and/or new schemas created as appropriate. Then export these workspaces and import them into QA and Production environments. | 2026-01-07 | 2026-01-07 | Y | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM
56 | 1 |  | 12 | Assign Workspace Administrators | In development assign a minimum of two Workspace administators to each workspace. These administrators will then be responsible for maintaining developer access within their own workspaces. | 2026-01-07 | 2026-01-07 | N | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM
57 | 2 | 11 | 6 | Prepare Course Outline | Creation of the training syllabus | 2026-01-03 | 2026-01-07 | Y | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM
58 | 2 | 11 | 6 | Write Training Guide | Produce the powerpoint deck (with notes) for the training instructor. | 2026-01-08 | 2026-01-10 | N | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM
59 | 2 | 11 | 6 | Develop Training Exercises | Create scripts for sample data and problem statements with solutions. | 2026-01-04 | 2026-01-10 | Y | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM
60 | 2 | 11 | 7 | Conduct Train-the-Trainer session | Give the training material to the selected developers. | 2026-01-11 | 2026-01-13 | Y | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM
61 | 2 | 12 | 7 | Train Developers I | Give the training to developers within your group. | 2026-01-14 | 2026-01-16 | Y | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM
62 | 2 | 12 | 8 | Train Developers II | Give the training to developers within your group. | 2026-01-16 | 2026-01-18 | Y | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM
63 | 3 | 13 | 3 | Create New Tables | Create table scripts to replicate the legacy tables | 2026-01-16 | 2026-01-16 | Y | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM
64 | 3 | 13 | 2 | Migrate data from Legacy Server | Develop scripts to populate the new database tables from the legacy database. | 2026-01-17 | 2026-01-20 | Y | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM
65 | 3 | 13 | 3 | Convert transaction logic | Convert the legacy database transactional objects across to the new database | 2026-01-17 | 2026-01-19 | Y | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM
66 | 3 | 14 | 4 | Redevelop Timesheet App | Develop desktop and mobile app for entering timesheets | 2026-01-19 | 2026-01-24 | Y | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM
67 | 3 | 14 | 8 | Create Shift Schedule App | Create an app for defining when people are scheduled to work different shifts. | 2026-01-19 | 2026-01-27 | Y | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM
68 | 3 | 14 | 8 | Reengineer Employee App | Create an app for employee details and benefits. | 2026-01-28 | 2026-01-30 | N | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM
69 | 3 | 15 | 9 | Customize Customer Tracker Packaged App | Install Customer Tracker and use flex fields to meet requirements. | 2026-01-30 | 2026-01-30 | Y | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM
70 | 3 | 15 | 9 | Migrate data into Customer Tracker tables | Move previous project tracking data into the Customer Tracker EBA_CUST_xxx tables. | 2026-01-31 | 2026-02-01 | Y | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM
71 | 3 | 15 | 11 | Pilot new Customer Tracker application | Use Customer Tracker to ensure it meets requirements. | 2026-02-02 | 2026-02-11 | N | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM
72 | 4 | 16 | 7 | Define scope of Partner Portal App. | Meet with internal and external SMEs and define the requirements | 2026-01-30 | 2026-02-06 | N | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM
73 | 4 | 16 | 8 | Define Partner App Data Structures | Design the data model for new and existing entities required to support the Partner Portal. | 2026-02-06 | 2026-02-09 | N | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM
74 | 4 | 16 | 6 | Design User Experience | Define how partners will interact with the application. | 2026-02-07 | 2026-02-08 | N | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM
75 | 4 | 17 | 2 | Develop Admin Screens for Partner Portal | Develop the screens needed to maintain all of the base tables for the Partner Portal app. | 2026-02-10 | 2026-02-12 | N | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM
76 | 4 | 17 | 12 | Populate Data Structures for Partner Portal | Upload sample data provided by key partner, and ensure existing tables accessible. | 2026-02-10 | 2026-02-11 | N | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM
77 | 4 | 17 | 6 | Design first-cut of main Partner Portal app | Implement the major functional areas and ensure navigation between pages is working correctly. | 2026-02-09 | 2026-02-13 | N | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM
78 | 4 | 17 | 7 | Present POC to Key Stakeholders | Walk key stakeholders through the proof of concept and obtain their feedback. | 2026-02-14 | 2026-02-14 | N | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM
79 | 5 | 18 | 7 | Define production scope of Partner Portal App. | Define the scope and timelines for the development of the production app. | 2026-02-15 | 2026-02-16 | N | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM
80 | 5 | 18 | 8 | Finalize Partner App Data Model | Refine the data model for new and existing entities required to support the Partner Portal. | 2026-02-15 | 2026-02-16 | N | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM
81 | 5 | 18 | 6 | Finalize User Experience | Write developer standards on UX and development standards on how partners will interact with the application. | 2026-02-15 | 2026-02-16 | N | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM
82 | 5 | 19 | 6 | Refine Admin Screens for Partner Portal | Refine screens developed in the POC to be fully operational to maintain all of the base tables for the Partner Portal app. | 2026-02-17 | 2026-02-20 | N | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM
83 | 5 | 19 | 5 | Populate Data Structures for Production Partner Portal | Upload actual data provided by key partner, and ensure existing tables accessible. | 2026-02-17 | 2026-02-19 | N | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM
84 | 5 | 19 | 7 | Design production screens for main Partner Portal app | Implement fully functional and complete screens to cover the major functional areas in Phase 1. | 2026-02-19 | 2026-02-25 | N | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM
85 | 5 | 20 | 10 | Train Partners | Train selected partners in how to use the Partner Portal app. | 2026-02-24 | 2026-02-24 | N | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM
86 | 5 | 20 | 4 | Monitor Partners | Monitor partners selected for the Beta and provide assistance as necessary. | 2026-02-25 | 2026-03-02 | N | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM
87 | 5 | 20 | 7 | Review Beta Feedback | Analyse feedback from the partners who participated in the Beta program. | 2026-03-03 | 2026-03-03 | N | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM
88 | 5 | 21 | 5 | Improve existing feature functions | Enhance existing features based on responses from Beta partners. | 2026-03-06 | 2026-03-25 | N | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM
89 | 5 | 21 | 3 | Add required feature functions | Add missing features outlined in responses from Beta partners. | 2026-03-06 | 2026-03-25 | N | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM
90 | 5 | 21 | 12 | Load full production data | Ensure all data required for production roll out are inserted and maintained. | 2026-03-20 | 2026-03-25 | N | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM
91 | 5 | 21 | 8 | Test Production Partner Portal | Do full scale testing on the Partner Portal application. | 2026-03-26 | 2026-03-30 | N | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM
92 | 5 | 22 | 3 | Install Partner Portal app onto Production Server | Install the database objects and application(s) into the production environment. | 2026-03-31 | 2026-03-31 | N | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM
93 | 5 | 22 | 12 | Configure production data load procedures | Install and test data load procedures from internal and external data sources into production environment. | 2026-04-01 | 2026-04-02 | N | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM
94 | 5 | 22 | 7 | Provide user credentials for partners | Define user credentials for each partner to allow access to the Partner Portal app. | 2026-04-02 | 2026-04-02 | N | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM
95 | 5 | 22 | 1 | Announce Partner Portal app to all partners | Email or call partners to inform them of the new application and instructions on how to get started. | 2026-04-03 | 2026-04-03 | N | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM | 2026-07-15 11:20 | ARCHIPATEL2632004@GMAIL.COM
1.1517e+38 | 1.1517e+38 | 1.1517e+38 | 2 | Task 1 | Testing tasks | 2026-07-15 | 2026-07-31 | Y | 2026-07-15 11:35 | ARCHI | 2026-07-15 11:36 | ARCHI
1.1518e+38 | 1.1518e+38 | 1.1518e+38 | 6 | TT1 | TT1 | 2026-07-16 | 2026-07-17 | Y | 2026-07-15 12:51 | ARCHI | 2026-07-15 12:51 | ARCHI