## Sheet1
ID | PROJECT | PARENT_TASK | TASK_NAME | ROW_VERSION_NUMBER | START_DATE | END_DATE | STATUS | ASSIGNED_TO | COST | BUDGET | CREATED | CREATED_BY | UPDATED | UPDATED_BY
41 | 9 | 40 | Develop web pages | 2 | 2026-05-24 04:31 | 2026-06-29 04:31 | On-Hold | Tiger Scott | 800 | 2000 | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM
42 | 9 | 40 | Purchase additional software licenses, if needed | 2 | 2026-07-01 04:31 | 2026-07-01 04:31 | On-Hold | Tom Suess | 0 | 100 | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM
43 | 1 | 3 | Investigate new Virus Protection software | 2 | 2026-05-12 04:31 | 2026-05-27 04:31 | Open | Pam King | 1700 | 1500 | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM
44 | 3 |  | Get RFPs for new server | 2 | 2026-04-26 04:31 | 2026-05-17 04:31 | Open | Mark Nile | 2000 | 1000 | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM
45 | 13 | 46 | Collect mission-critical spreadsheets | 2 | 2026-04-28 04:31 | 2026-06-29 04:31 | Open | Pam King | 2500 | 4000 | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM
46 | 13 |  | Create applications from spreadsheets | 2 | 2026-04-28 04:31 | 2026-10-12 04:31 | Open | Pam King | 6000 | 10000 | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM
47 | 13 | 46 | Lock spreadsheets | 2 | 2026-04-28 04:31 | 2026-10-12 04:31 | Open | Pam King | 1000 | 800 | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM
48 | 13 | 46 | Send links to previous spreadsheet owners | 2 | 2026-04-29 04:31 | 2026-10-14 04:31 | Open | Pam King | 1000 | 1500 | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM
49 | 2 |  | Customize solutions | 2 | 2026-04-21 04:31 | 2026-07-14 04:31 | Open | John Watson | 1500 | 4000 | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM
50 | 2 | 49 | Train developers / users | 2 | 2026-05-24 04:31 | 2026-08-07 04:31 | Pending | John Watson | 0 | 8000 | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM
51 | 2 | 49 | Implement in Production | 2 | 2026-05-10 04:31 | 2026-09-15 04:31 | Open | John Watson | 200 | 1500 | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM
52 | 7 | 53 | Migrate applications | 2 | 2026-04-28 04:31 | 2026-07-04 04:31 | Open | Mark Nile | 1000 | 8000 | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM
53 | 7 |  | Plan migration schedule | 2 | 2026-05-05 04:31 | 2026-07-16 04:31 | Open | Mark Nile | 1500 | 6000 | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM
54 | 10 | 33 | Publish Feedback application | 2 | 2026-05-09 04:31 | 2026-09-16 04:31 | Open | Pam King | 300 | 12000 | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM
55 | 6 | 18 | Train developers on tracking bugs | 2 | 2026-06-03 04:31 | 2026-07-23 04:31 | On-Hold | Myra Sutcliff | 0 | 2000 | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM
56 | 7 | 53 | End-user Training | 2 | 2026-05-11 04:31 | 2026-07-06 04:31 | Open | John Watson | 0 | 2000 | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM
57 | 11 | 61 | Identify server requirements | 2 | 2026-03-15 04:31 | 2026-03-16 04:31 | Closed | John Watson | 100 | 200 | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM
58 | 11 | 61 | Specify security authentication scheme(s) | 2 | 2026-03-17 04:31 | 2026-03-19 04:31 | Closed | John Watson | 200 | 300 | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM
60 | 11 | 61 | Create pilot workspace | 2 | 2026-03-24 04:31 | 2026-03-24 04:31 | Closed | John Watson | 100 | 100 | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM
61 | 11 |  | Configure Workspace provisioning | 2 | 2026-03-24 04:31 | 2026-03-24 04:31 | Closed | John Watson | 200 | 100 | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM
62 | 11 | 57 | Run installation | 2 | 2026-03-25 04:31 | 2026-03-25 04:31 | Closed | James Cassidy | 100 | 100 | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM
64 | 14 | 67 | Obtain equipment specifications | 2 | 2026-05-17 04:31 | 2026-05-20 04:31 | Pending | James Cassidy | 0 | 500 | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM
65 | 3 | 44 | Purchase backup server | 2 | 2026-05-26 04:31 | 2026-06-21 04:31 | Pending | Mark Nile | 0 | 3000 | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM
66 | 14 | 67 | Identify integration points | 2 | 2026-05-22 04:31 | 2026-06-11 04:31 | Pending | Mark Nile | 0 | 2000 | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM
67 | 14 |  | Decommission machines | 2 | 2026-05-22 04:31 | 2026-05-22 04:31 | Pending | Scott Spencer | 0 | 100 | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM
68 | 14 | 67 | Map data usage | 2 | 2026-06-03 04:31 | 2026-07-16 04:31 | Pending | Mark Nile | 0 | 8000 | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM
69 | 14 | 67 | Purchase new machines | 2 | 2026-07-08 04:31 | 2026-08-02 04:31 | Pending | John Watson | 0 | 2500 | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM
70 | 14 | 67 | Import data | 2 | 2026-07-09 04:31 | 2026-08-05 04:31 | Pending | John Watson | 0 | 1000 | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM
71 | 14 | 67 | Convert processes | 2 | 2026-06-16 04:31 | 2026-08-14 04:31 | Pending | Pam King | 0 | 3000 | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM
74 | 14 |  | Decommission servers | 2 | 2026-06-15 04:31 | 2026-09-12 04:31 | Pending | Al Bines | 0 | 500 | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM
75 | 6 | 18 | Measure effectiveness of improved QA | 2 | 2026-06-15 04:31 | 2026-07-15 04:31 | Pending | Myra Sutcliff | 0 | 1500 | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM
76 | 10 | 33 | Response to Customer Feedback | 2 | 2026-06-15 04:31 | 2026-10-07 04:31 | Pending | Russ Saunders | 0 | 6000 | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM
77 | 10 | 33 | User acceptance testing | 2 | 2026-06-30 04:31 | 2026-10-02 04:31 | Pending | Russ Saunders | 0 | 2500 | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM
78 | 10 | 79 | End-user Training | 2 | 2026-08-02 04:31 | 2026-10-14 04:31 | Pending | Myra Sutcliff | 0 | 2500 | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM
79 | 10 | 32 | Rollout sample applications | 2 | 2026-10-05 04:31 | 2026-10-16 04:31 | Pending | Pam King | 0 | 500 | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM
72 | 14 | 67 | Installation | 2 | 2026-06-17 04:31 | 2026-07-17 04:31 | Pending | Mark Nile | 0 | 1500 | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM
73 | 14 | 67 | Notify users | 2 | 2026-07-19 04:31 | 2026-07-22 04:31 | Pending | Mark Nile | 0 | 200 | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM
34 | 10 | 32 | Plan production release schedule | 2 | 2026-05-05 04:31 | 2026-05-05 04:31 | Closed | Pam King | 100 | 100 | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM
37 | 12 | 38 | Complete questionnaire | 2 | 2026-05-01 04:31 | 2025-05-15 04:31 | On-Hold | Irene Jones | 1200 | 800 | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM
59 | 11 | 61 | Select servers for Development, Test, Production | 2 | 2026-03-17 04:31 | 2026-03-22 04:31 | Closed | James Cassidy | 200 | 600 | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM
3 | 1 |  | HR Support Systems | 2 | 2026-03-15 04:31 | 2026-07-25 04:31 | Closed | Al Bines | 300 | 500 | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM
1 | 1 | 3 | HR software upgrades | 2 | 2026-03-15 04:31 | 2026-07-11 04:31 | On-Hold | Pam King | 8000 | 7000 | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM
2 | 1 | 3 | Arrange for vacation coverage | 2 | 2026-03-15 04:31 | 2026-05-14 04:31 | On-Hold | Russ Sanders | 9500 | 7000 | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM
4 | 3 | 44 | Complete plan | 2 | 2026-03-22 04:31 | 2026-04-27 04:31 | Closed | Mark Nile | 3000 | 1500 | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM
5 | 3 | 44 | Check software licenses | 2 | 2026-04-25 04:31 | 2026-04-26 04:31 | Closed | Mark Nile | 200 | 200 | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM
6 | 5 | 36 | Create training workspace | 2 | 2026-04-14 04:31 | 2026-04-21 04:31 | Closed | James Cassidy | 500 | 700 | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM
7 | 5 | 36 | Publish links to self-study courses | 2 | 2026-04-14 04:31 | 2026-04-14 04:31 | Closed | John Watson | 100 | 100 | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM
8 | 2 | 49 | Identify point solutions required | 2 | 2026-04-16 04:31 | 2026-04-18 04:31 | Closed | John Watson | 200 | 300 | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM
9 | 2 | 49 | Install in development | 2 | 2026-04-20 04:31 | 2026-04-20 04:31 | Closed | John Watson | 100 | 100 | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM
15 | 4 | 17 | Identify owners | 2 | 2026-04-02 04:31 | 2026-04-05 04:31 | Closed | Hank Davis | 250 | 300 | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM
16 | 4 | 17 | Initial Draft Review | 2 | 2026-04-06 04:31 | 2026-04-06 04:31 | Closed | Hank Davis | 100 | 100 | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM
17 | 4 |  | Monitor Review Comments | 2 | 2026-04-06 04:31 | 2026-05-14 04:31 | Closed | Hank Davis | 450 | 500 | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM
18 | 6 |  | Implement bug tracking software | 2 | 2026-03-29 04:31 | 2026-03-29 04:31 | Closed | Myra Sutcliff | 100 | 100 | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM
19 | 6 | 18 | Review automated testing tools | 2 | 2026-03-30 04:31 | 2026-04-28 04:31 | Closed | Myra Sutcliff | 2750 | 1500 | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM
20 | 7 | 53 | Identify pilot applications | 2 | 2026-03-24 04:31 | 2026-03-29 04:31 | Closed | Mark Nile | 300 | 500 | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM
21 | 7 | 53 | Migrate pilot applications to | 2 | 2026-04-03 04:31 | 2026-04-08 04:31 | Closed | Mark Nile | 500 | 500 | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM
22 | 8 | 28 | Customize Software Projects software | 2 | 2027-04-29 04:31 | 2026-06-03 04:31 | Open | Tom Suess | 600 | 1000 | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM
23 | 7 | 53 | Post-migration review | 2 | 2026-04-14 04:31 | 2026-04-14 04:31 | Closed | Mark Nile | 100 | 100 | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM
24 | 7 | 23 | User acceptance testing | 2 | 2026-04-16 04:31 | 2026-04-17 04:31 | Closed | Mark Nile | 600 | 200 | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM
25 | 8 | 28 | Enter base data (Projects, Milestones, etc.) | 2 | 2026-04-23 04:31 | 2026-04-24 04:31 | Closed | Tom Suess | 200 | 200 | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM
26 | 8 | 28 | Load current tasks and enhancements | 2 | 2026-04-25 04:31 | 2026-04-29 04:31 | Closed | Tom Suess | 400 | 500 | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM
27 | 6 | 18 | Document quality assurance procedures | 2 | 2026-04-29 04:31 | 2026-06-02 04:31 | On-Hold | Myra Sutcliff | 3500 | 4000 | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM
28 | 8 |  | Conduct project kickoff meeting | 2 | 2026-04-18 04:31 | 2026-04-18 04:31 | Closed | Pam King | 100 | 100 | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM
29 | 9 | 40 | Determine host server | 2 | 2026-04-19 04:31 | 2026-04-20 04:31 | Closed | Tiger Scott | 200 | 200 | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM
30 | 9 | 40 | Check software licenses | 2 | 2026-04-20 04:31 | 2026-04-20 04:31 | Closed | Tom Suess | 100 | 100 | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM
31 | 10 | 33 | Identify pilot users | 2 | 2026-04-18 04:31 | 2026-04-19 04:31 | Closed | Scott Spencer | 200 | 200 | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM
32 | 10 | 33 | Software Deliverable | 2 | 2026-04-20 04:31 | 2026-05-03 04:31 | Closed | Scott Spencer | 400 | 500 | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM
33 | 10 |  | Early Adopter Release | 2 | 2026-05-04 04:31 | 2026-05-04 04:31 | Closed | Pam King | 100 | 100 | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM
35 | 11 | 61 | Determine midtier configuration(s) | 2 | 2026-03-16 04:31 | 2026-03-16 04:31 | Closed | James Cassidy | 100 | 100 | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM
36 | 5 |  | Manage Training Activities | 2 | 2026-04-11 04:31 | 2026-06-17 04:31 | On-Hold | John Watson | 1000 | 2000 | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM
38 | 12 |  | Review feedback | 2 | 2026-05-23 04:31 | 2026-05-29 04:31 | On-Hold | Irene Jones | 200 | 400 | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM
39 | 12 | 38 | Plan rollout schedule | 2 | 2026-05-30 04:31 | 2026-06-07 04:31 | On-Hold | Irene Jones | 0 | 750 | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM
40 | 9 |  | Plan rollout schedule | 2 | 2026-04-23 04:31 | 2026-05-16 04:31 | On-Hold | Al Bines | 300 | 1000 | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM | 2026-05-15 04:31 | ARCHIPATEL2632004@GMAIL.COM